## Sheet 1 - Jira-2
Jira-2
Summary | Issue key | Issue id | Sprint | Issue Type | Story Points | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Description | Environment | Watchers | Watchers | Watchers Id | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Outward issue link (Blocks) | Attachment | Custom field (Development) | Custom field (Issue color) | Custom field (Rank) | Custom field (Start date) | Comment | Comment | Comment | Parent | Parent summary | Status Category
Ongoing Edge Cases for FCF Evaluations - Create Individual Bugs for Tickers | STOCKO-114 | 10133 |  | Story |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 23/Sep/21 8:27 PM | 23/Sep/21 8:27 PM | 28/Sep/21 11:07 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000nb: | [6 empty] | To Do
Create 5 Test Cases | STOCKO-113 | 10132 | STOCKO Sprint 1 | Ticket | 5 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Highest | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 23/Sep/21 8:23 PM | 28/Sep/21 4:56 AM | 23/Sep/21 8:25 PM | 28/Sep/21 4:56 AM |  | 0 |  | * 2 Tickers Tests * 1 Log in and Log Out Test * API End Point Test for Database and Flask * 1 Positions Test Case |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j:04i | [6 empty] | Done
FCF evaluation edge cases for ticker BABA | STOCKO-112 | 10131 | STOCKO Sprint 2 | Bug | 2 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 23/Sep/21 8:20 PM | 27/Sep/21 3:08 PM | 27/Sep/21 3:07 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000mv: | [6 empty] | To Do
FCF Bug - Found when testing CIM Ticker | STOCKO-111 | 10130 | STOCKO Sprint 1 | Bug | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 23/Sep/21 8:14 PM | 24/Sep/21 2:38 PM | 23/Sep/21 8:14 PM | 24/Sep/21 2:38 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [10 empty] | 23/Sep/21 8:15 PM;ug:8f155933-eee4-4041-b0d1-580ec09c362d;Screen Shot 2021-09-23 at 3.15.00 PM.png;https://housing.atlassian.net/secure/attachment/10001/Screen+Shot+2021-09-23+at+3.15.00+PM.png | {} |  | 0¦i0001j:2 | [6 empty] | Done
Error when searching CIM ticker | STOCKO-110 | 10129 | STOCKO Sprint 2 | Bug | 1 | Obsolete | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 6:35 PM | 27/Sep/21 3:26 PM | 27/Sep/21 3:25 PM | 27/Sep/21 3:26 PM |  | 0 |  |  |  | Alex Davis | Brendan Lucich | 5b86f28907d9482bd98ae887 | 60c2917a946928007011d4ae | [10 empty] | {} |  | 0¦i000mf: |  | 27/Sep/21 3:26 PM;60c2917a946928007011d4ae;Duplicate of [https://housing.atlassian.net/browse/STOCKO-111¦https://housing.atlassian.net/browse/STOCKO-111¦smart-link] resolved in sprint 1 |  |  |  |  | Done
Ability to get necessary metrics from AV API Requests for Spring 3 Deliverables. | STOCKO-109 | 10128 | STOCKO Sprint 3 | Story |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 6:10 PM | 23/Sep/21 6:10 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000m7: | [6 empty] | To Do
Abillity to get necessary metrics from AV API Requests for Spring 2 Deliverables | STOCKO-108 | 10127 | STOCKO Sprint 2 | Story | 3 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Brendan Lucich | 60c2917a946928007011d4ae | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 6:07 PM | 23/Sep/21 6:09 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000lz: | [6 empty] | To Do
Front end webdesign sketching | STOCKO-107 | 10126 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:53 PM | 23/Sep/21 6:00 PM | 28/Sep/21 11:09 AM | 23/Sep/21 5:53 PM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000lr: | [6 empty] | Done
Navbar and Routing for the App side of the page | STOCKO-106 | 10125 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:52 PM | 27/Sep/21 7:10 PM | 28/Sep/21 11:09 AM | 27/Sep/21 7:10 PM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001o:zq | [6 empty] | Done
Connect Flask to the front end | STOCKO-105 | 10124 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:50 PM | 28/Sep/21 4:56 AM | 28/Sep/21 11:09 AM | 28/Sep/21 4:56 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001o:zj | [6 empty] | Done
Connect Flask to databses | STOCKO-104 | 10123 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:50 PM | 28/Sep/21 1:01 AM | 28/Sep/21 11:09 AM | 28/Sep/21 1:01 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001j:1i | [6 empty] | Done
Write flask functions for sprint one deliverables | STOCKO-103 | 10122 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:50 PM | 28/Sep/21 4:58 AM | 28/Sep/21 11:09 AM | 28/Sep/21 4:58 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001j:00r | [6 empty] | Done
Connect positions data with Login Database | STOCKO-102 | 10121 | STOCKO Sprint 2 | Ticket | 3 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Brady Mack | 5e1f420fd152ca0c9e193703 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:50 PM | 28/Sep/21 4:57 AM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000kn: | [6 empty] | To Do
Connect login data with Database | STOCKO-101 | 10120 | STOCKO Sprint 2 | Ticket | 5 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Brady Mack | 5e1f420fd152ca0c9e193703 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:49 PM | 28/Sep/21 4:57 AM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000kf: | [6 empty] | To Do
Create the positions front end UI | STOCKO-100 | 10119 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:49 PM | 27/Sep/21 7:10 PM | 28/Sep/21 11:09 AM | 27/Sep/21 7:10 PM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001o:zm | [6 empty] | Done
Create the Evaluations Front End UI | STOCKO-99 | 10118 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:49 PM | 27/Sep/21 7:10 PM | 28/Sep/21 11:09 AM | 27/Sep/21 7:10 PM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001o:zk | [6 empty] | Done
Connect the Positions to the front end | STOCKO-98 | 10117 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:48 PM | 28/Sep/21 4:57 AM | 28/Sep/21 11:09 AM | 28/Sep/21 4:57 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001j:00i | [6 empty] | Done
Connect Stock Evaluations to the Front End | STOCKO-97 | 10116 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:48 PM | 28/Sep/21 4:57 AM | 28/Sep/21 11:09 AM | 28/Sep/21 4:57 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001j:01 | [6 empty] | Done
Login requirement for app side of website | STOCKO-96 | 10115 | STOCKO Sprint 2 | Ticket | 5 | Testing | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:48 PM | 28/Sep/21 1:12 AM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i000bt: | [6 empty] | In Progress
2-3 Minute Demo | STOCKO-95 | 10114 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 23/Sep/21 5:47 PM | 28/Sep/21 4:56 AM | 28/Sep/21 11:09 AM | 28/Sep/21 4:56 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001j:02 | [6 empty] | Done
On refresh github sends to 404.html | STOCKO-94 | 10113 | STOCKO Sprint 1 | Bug | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 22/Sep/21 4:59 PM | 24/Sep/21 2:26 AM | 28/Sep/21 11:09 AM | 24/Sep/21 2:26 AM |  | 0 |  |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001o:zzr | [6 empty] | Done
Ability to get necessary metrics from AV API Requests for Sprint 2 Deliverables | STOCKO-93 | 10099 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 21/Sep/21 5:10 PM | 21/Sep/21 5:10 PM | 21/Sep/21 5:10 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000fr: | [6 empty] | To Do
Get Price to Book Value Ratio for Pillars | STOCKO-92 | 10098 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 16/Sep/21 6:38 PM | 21/Sep/21 5:07 PM | 16/Sep/21 7:48 PM | 21/Sep/21 5:07 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j:i | [6 empty] | Done
Add First Stand up Notes and Project Documents to Wiki | STOCKO-91 | 10097 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 16/Sep/21 5:22 PM | 16/Sep/21 5:22 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000fj: | [6 empty] | To Do
Add First Stand Up Notes and Project Documents to Box | STOCKO-90 | 10096 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 16/Sep/21 5:22 PM | 16/Sep/21 5:22 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000fb: | [6 empty] | To Do
Bootstrap a Wiki Page | STOCKO-89 | 10095 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 16/Sep/21 5:21 PM | 16/Sep/21 5:21 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000f3: | [6 empty] | To Do
Get EV/EBITDA Ratio for Pillars | STOCKO-88 | 10094 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 16/Sep/21 5:21 PM | 21/Sep/21 5:07 PM | 16/Sep/21 6:33 PM | 21/Sep/21 5:07 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002p:r | [6 empty] | Done
Setup program to use API to source pricing data for DB | STOCKO-87 | 10093 | STOCKO Sprint 1 | Story | 13 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 14/Sep/21 5:56 PM | 27/Sep/21 1:12 PM | 28/Sep/21 11:09 AM | 27/Sep/21 1:12 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:6 | [6 empty] | Done
The user wants to be able to log out of the app and log in to another account | STOCKO-86 | 10092 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 8:00 PM | 13/Sep/21 8:01 PM | 13/Sep/21 8:01 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000en: | [6 empty] | To Do
Security - Auto log out after period of inactivity | STOCKO-85 | 10091 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 8:00 PM | 13/Sep/21 8:00 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000ef: | [6 empty] | To Do
The user wants to be able to understand the project in a home page | STOCKO-84 | 10090 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:56 PM | 13/Sep/21 7:56 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000e7: | [6 empty] | To Do
The user wants to be able to overview the project in an about page | STOCKO-83 | 10089 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:55 PM | 13/Sep/21 7:55 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000dz: | [6 empty] | To Do
The user wants to be able to contact the developers | STOCKO-82 | 10088 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:55 PM | 13/Sep/21 7:55 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000dr: | [6 empty] | To Do
The user wants to be able to view the back testing for out value investing methodology | STOCKO-81 | 10087 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:54 PM | 13/Sep/21 7:54 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000dj: | [6 empty] | To Do
The user wants to be able to forecast a stock price | STOCKO-80 | 10086 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:54 PM | 13/Sep/21 7:54 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000db: | [6 empty] | To Do
Front End UI Banner Work | STOCKO-79 | 10085 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:54 PM | 13/Sep/21 7:54 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000d3: | [6 empty] | To Do
NLP on analyst projections | STOCKO-78 | 10084 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:53 PM | 13/Sep/21 7:53 PM | 13/Sep/21 7:59 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000cv: | [6 empty] | To Do
The user wants to be able view the raw company data | STOCKO-77 | 10083 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:53 PM | 13/Sep/21 7:53 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000cn: | [6 empty] | To Do
The user wants to be able to view the historical price in chart form | STOCKO-76 | 10082 |  | Ticket |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 7:51 PM | 13/Sep/21 7:52 PM | 13/Sep/21 7:52 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i000cf: | [6 empty] | To Do
Bug With Apple Look Up | STOCKO-75 | 10081 | STOCKO Sprint 1 | Bug |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 4:31 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:16 AM | 23/Sep/21 8:22 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [10 empty] | 13/Sep/21 4:30 PM;ug:8f155933-eee4-4041-b0d1-580ec09c362d;Screen Shot 2021-09-13 at 11.30.22 AM.png;https://housing.atlassian.net/secure/attachment/10000/Screen+Shot+2021-09-13+at+11.30.22+AM.png | {} |  | 0¦i0001b:0i |  | 14/Sep/21 4:29 PM;60c2917a946928007011d4ae;Need to try and recreate | 23/Sep/21 8:22 PM;60c2917a946928007011d4ae;This will be looked at when making test cases, however issue has not reappeared, moving to obsolete |  |  |  | Done
Error Checking for 5 Years of History | STOCKO-74 | 10080 | STOCKO Sprint 1 | Bug | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 13/Sep/21 3:44 PM | 14/Sep/21 5:31 PM | 13/Sep/21 3:44 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002q:v | [6 empty] | Done
[Enabler] Explore the difference between Hand Calculated PE Ratio and API Given PE Ratio | STOCKO-73 | 10079 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 10/Sep/21 3:13 PM | 27/Sep/21 3:08 PM | 10/Sep/21 3:13 PM | 27/Sep/21 3:08 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j:06 | [6 empty] | Done
Get Current Shares Outstanding | STOCKO-72 | 10078 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 09/Sep/21 9:19 PM | 14/Sep/21 5:31 PM | 09/Sep/21 9:19 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002p:i | [6 empty] | Done
Create Balance Sheet Schema | STOCKO-71 | 10077 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 09/Sep/21 7:28 PM | 14/Sep/21 5:26 PM | 09/Sep/21 7:28 PM | 14/Sep/21 5:26 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002q:i | [6 empty] | Done
Create Cash Flow Schema | STOCKO-70 | 10076 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 09/Sep/21 6:55 PM | 14/Sep/21 5:26 PM | 28/Sep/21 11:09 AM | 14/Sep/21 5:26 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002q: | [6 empty] | Done
Create Income Statement Schema | STOCKO-69 | 10075 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 09/Sep/21 6:55 PM | 14/Sep/21 5:26 PM | 28/Sep/21 11:09 AM | 14/Sep/21 5:26 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002p: | [6 empty] | Done
Create Company Overview Schema | STOCKO-68 | 10074 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 09/Sep/21 6:54 PM | 14/Sep/21 5:26 PM | 28/Sep/21 11:09 AM | 14/Sep/21 5:26 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002o: | [6 empty] | Done
Create dev, test, and prod DB collections | STOCKO-67 | 10073 | STOCKO Sprint 1 | Story | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:20 PM | 08/Sep/21 11:20 PM | 28/Sep/21 11:09 AM | 08/Sep/21 11:20 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002r: | [6 empty] | Done
Connect Authentication to DB | STOCKO-66 | 10072 | STOCKO Sprint 2 | Story | 13 | In Progress | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:18 PM | 27/Sep/21 7:37 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Andrew Setka | Brady Mack | 5b86f0acfa38ae2c89607b8b | 5e1f420fd152ca0c9e193703 | [10 empty] | {} |  | 0¦i000br: |  | 27/Sep/21 7:37 PM;5b86f0acfa38ae2c89607b8b;punted to sprint 2 for now |  |  |  |  | In Progress
Connect Authentication to Frontend | STOCKO-65 | 10071 | STOCKO Sprint 1 | Story | 13 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:18 PM | 27/Sep/21 4:13 AM | 28/Sep/21 11:09 AM | 27/Sep/21 4:13 AM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001k:9 | [6 empty] | Done
Initialize Authentication Platform | STOCKO-64 | 10070 | STOCKO Sprint 1 | Story | 8 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:16 PM | 12/Sep/21 10:40 PM | 28/Sep/21 11:09 AM | 12/Sep/21 10:40 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001k:r | [6 empty] | Done
Determine Login Solution | STOCKO-63 | 10069 | STOCKO Sprint 1 | Story | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:13 PM | 12/Sep/21 10:39 PM | 28/Sep/21 11:09 AM | 12/Sep/21 10:39 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001k:i | [6 empty] | Done
Get Stock Price from Ticker | STOCKO-62 | 10068 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:04 PM | 14/Sep/21 5:31 PM | 09/Sep/21 7:45 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:r | [6 empty] | Done
Get Free Cash Flow Evaluation for Pillars | STOCKO-61 | 10067 | STOCKO Sprint 1 | Ticket | 5 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:04 PM | 23/Sep/21 8:26 PM | 23/Sep/21 8:25 PM | 23/Sep/21 8:26 PM |  | 0 |  |  |  | Brady Mack | Brendan Lucich | 5e1f420fd152ca0c9e193703 | 60c2917a946928007011d4ae | [10 empty] | {} |  | 0¦i0001j:4 |  | 09/Sep/21 8:24 PM;60c2917a946928007011d4ae;Cash Flow * Wanted PE Ratio vs Current Market Cap | 23/Sep/21 8:26 PM;60c2917a946928007011d4ae;This will have on going edge cases but will be deal with as found |  |  |  | Done
Get Free Cash Flow Growth for Pillars | STOCKO-60 | 10066 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:03 PM | 14/Sep/21 5:31 PM | 10/Sep/21 3:38 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:t | [6 empty] | Done
Get Total Assets vs. Liabilities for Pillars | STOCKO-59 | 10065 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:03 PM | 14/Sep/21 5:31 PM | 09/Sep/21 8:23 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:m | [6 empty] | Done
Get Change in Shares Outstanding for Pillars | STOCKO-58 | 10064 | STOCKO Sprint 2 | Ticket | 1 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Highest |  | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:02 PM | 23/Sep/21 6:07 PM | 23/Sep/21 6:07 PM |  |  | 0 | Blocked |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002x: | [6 empty] | To Do
Get Current Assets vs. Liabilities for Pillars | STOCKO-57 | 10063 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:02 PM | 14/Sep/21 5:31 PM | 09/Sep/21 8:24 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:k | [6 empty] | Done
Get Revenue Growth for Pillars | STOCKO-56 | 10062 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:02 PM | 14/Sep/21 5:31 PM | 09/Sep/21 8:24 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:l | [6 empty] | Done
Get Profit Growth for Pillars | STOCKO-55 | 10061 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:02 PM | 14/Sep/21 5:31 PM | 09/Sep/21 8:08 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:li | [6 empty] | Done
Get Profit Margin for Pillars | STOCKO-54 | 10060 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:01 PM | 14/Sep/21 5:31 PM | 09/Sep/21 8:08 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:ki | [6 empty] | Done
Get PE Ratio for Pillars | STOCKO-53 | 10059 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 11:01 PM | 14/Sep/21 5:31 PM | 09/Sep/21 7:58 PM | 14/Sep/21 5:31 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0002q:u | [6 empty] | Done
Create DB Support for Adding and Editing Prices | STOCKO-52 | 10058 | STOCKO Sprint 1 | Story | 8 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:50 PM | 28/Sep/21 1:01 AM | 28/Sep/21 11:09 AM | 28/Sep/21 1:01 AM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:05 | [6 empty] | Done
Create Pricing Collection in DB for Prices | STOCKO-51 | 10057 | STOCKO Sprint 1 | Story | 8 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:49 PM | 27/Sep/21 1:12 PM | 28/Sep/21 11:09 AM | 27/Sep/21 1:12 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:1 | [6 empty] | Done
Add DB Support for Editing Positions | STOCKO-50 | 10056 | STOCKO Sprint 1 | Story | 8 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done |  |  | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:48 PM | 27/Sep/21 1:12 PM | 28/Sep/21 11:09 AM | 27/Sep/21 1:12 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:04 | [6 empty] | Done
Add DB Support for Creating Users | STOCKO-49 | 10055 | STOCKO Sprint 1 | Story | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:48 PM | 27/Sep/21 1:12 PM | 28/Sep/21 11:09 AM | 27/Sep/21 1:12 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:09 | [6 empty] | Done
Add DB Support for Adding Positions | STOCKO-48 | 10054 | STOCKO Sprint 1 | Story | 5 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:47 PM | 27/Sep/21 1:12 PM | 28/Sep/21 11:09 AM | 27/Sep/21 1:12 PM |  | 0 |  |  |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001j:0i | [6 empty] | Done
Request Premium Amount of API Calls | STOCKO-47 | 10053 | STOCKO Sprint 1 | Story | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | Brady Mack | 5e1f420fd152ca0c9e193703 | 08/Sep/21 10:45 PM | 08/Sep/21 10:46 PM | 28/Sep/21 11:09 AM | 08/Sep/21 10:45 PM |  | 0 |  | Need more than 5/min provided by the company in the free plan |  | Brady Mack |  | 5e1f420fd152ca0c9e193703 | [11 empty] | {} |  | 0¦i0001m: | [6 empty] | Done
Linking front end with backend | STOCKO-41 | 10047 | STOCKO Sprint 1 | Story |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Highest | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | Alex Davis | 5b86f28907d9482bd98ae887 | 07/Sep/21 9:07 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:15 AM | 23/Sep/21 6:04 PM |  | 0 | Obsolete |  |  | Alex Davis |  | 5b86f28907d9482bd98ae887 | [11 empty] | {} |  | 0¦i0001b:2 | [6 empty] | Done
Change In Shares Outstanding Incorrect | STOCKO-40 | 10046 | STOCKO Sprint 2 | Bug | 8 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Highest |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 06/Sep/21 10:17 PM | 23/Sep/21 6:08 PM | 23/Sep/21 6:07 PM |  |  | 0 |  | Stock splits/reversals do not change past shares outstanding values in the api request so they will need to be tracked for the last 5 years and changed manually |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i00031:i | [6 empty] | To Do
FCF evaluation edge cases | STOCKO-39 | 10045 | STOCKO Sprint 1 | Bug |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 02/Sep/21 2:42 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:15 AM | 23/Sep/21 8:20 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [9 empty] | STOCKO-61 |  | {} |  | 0¦i0001b:4 |  | 22/Sep/21 4:32 PM;60c2917a946928007011d4ae;BABA Valuations | 23/Sep/21 8:19 PM;60c2917a946928007011d4ae;This is an ongoing issue and will come up as we test more and more stocks, thinking about just making individual bug tickets as we discover them |  |  |  | Done
Find the intrinsic value of a stock | STOCKO-38 | 10044 | STOCKO Sprint 1 | Ticket |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 02/Sep/21 2:41 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:15 AM | 14/Sep/21 4:25 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001b:1 | [6 empty] | Done
First Set of Backend Processing on AV API Data (Original Set of Metrics) | STOCKO-37 | 10043 | STOCKO Sprint 1 | Ticket |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 02/Sep/21 2:30 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:14 AM | 08/Sep/21 7:21 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001d: |  | 02/Sep/21 2:37 PM;60c2917a946928007011d4ae;* {noformat}# pe ratio + # profit margin + # profit growth + # revenue growth + # current assets vs liabilities + # shares outstanding + # cash flow growth + # cash flow * wanted pe ratio vs current market caps +/- # stock price +{noformat} |  |  |  |  | Done
Ability to get necessary metrics from AV API Requests for Sprint 1 Deliverables | STOCKO-36 | 10042 | STOCKO Sprint 1 | Ticket | 5 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 02/Sep/21 2:30 PM | 23/Sep/21 6:07 PM | 23/Sep/21 6:06 PM | 23/Sep/21 6:07 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j:9 |  | 09/Sep/21 6:57 PM;60c2917a946928007011d4ae;Calculations on top of new data schema | 10/Sep/21 3:05 PM;60c2917a946928007011d4ae;Sort of an enabler. Reaching out to finance professors and graduate students | 21/Sep/21 5:09 PM;60c2917a946928007011d4ae;This ticket is probably in the final stage for sprint 1 deliverables. Shares outstanding is a huge ticket attached with a bug that needs to be developed, however all communication with experts has been done for sprint 1. This will be a new ticket in sprint 2 most likely. |  |  | Done
Test API Requests from Alpha Vantage (Original Data Dictionary) | STOCKO-35 | 10041 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 02/Sep/21 2:27 PM | 09/Sep/21 6:56 PM | 28/Sep/21 11:09 AM | 02/Sep/21 2:31 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002i: | [6 empty] | Done
[Enabler] Page Limitations on Github | STOCKO-34 | 10040 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 6:19 PM | 27/Sep/21 4:19 AM | 28/Sep/21 11:09 AM | 27/Sep/21 4:19 AM |  | 0 |  | Research routing limitations for hosting on Github if that is the requirement |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001o:zi | [6 empty] | Done
Bootstrap APIs | STOCKO-33 | 10039 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 6:15 PM | 26/Aug/21 6:15 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0006b: | [6 empty] | To Do
Create FLASK API that can handle generic GET/POST Requests | STOCKO-32 | 10038 | STOCKO Sprint 1 | Subtask |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 6:12 PM | 28/Sep/21 6:17 AM | 28/Sep/21 6:17 AM | 26/Aug/21 6:16 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0007z: |  |  |  |  | 10011 | Bootstrap Flask API to Run Locally | Done
Bootstrap Repo and Website | STOCKO-31 | 10037 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 6:07 PM | 26/Aug/21 6:15 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0005v: | [6 empty] | To Do
Stock Back-Testing | STOCKO-30 | 10036 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:45 PM | 26/Aug/21 5:45 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0007j: | [6 empty] | To Do
Assignments/Presentations | STOCKO-29 | 10035 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:41 PM | 26/Aug/21 5:41 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0007b: | [6 empty] | To Do
Positions DB | STOCKO-28 | 10034 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:41 PM | 26/Aug/21 6:17 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0006d: | [6 empty] | To Do
Backend to Datasource API/Webscrapping | STOCKO-27 | 10033 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:40 PM | 26/Aug/21 5:40 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0006v: | [6 empty] | To Do
Backend to Frontend API | STOCKO-26 | 10032 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:40 PM | 26/Aug/21 5:40 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0006n: | [6 empty] | To Do
Backend Stock Processing | STOCKO-25 | 10031 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:40 PM | 26/Aug/21 5:40 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} | purple | 0¦i0006f: | [6 empty] | To Do
Website App Frontend/UI | STOCKO-24 | 10030 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:39 PM | 26/Aug/21 6:17 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0007r: | [6 empty] | To Do
User Accounts | STOCKO-23 | 10029 |  | Epic |  | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:39 PM | 26/Aug/21 6:17 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0006c: | [6 empty] | To Do
[Enabler] Mock Diagram/Architecture/Resources for Login Authentication, Storage, Access | STOCKO-22 | 10028 | STOCKO Sprint 1 | Ticket |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:36 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:14 AM | 27/Sep/21 4:15 AM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001b:i |  |  |  |  | 10029 | User Accounts | Done
PWEB Draft Due 9/24 at 2:00 pm | STOCKO-21 | 10027 | STOCKO Sprint 1 | Story | 8 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Highest | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:34 PM | 26/Sep/21 9:09 PM | 22/Sep/21 4:19 PM | 26/Sep/21 9:09 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001q:d |  |  |  |  | 10035 | Assignments/Presentations | Done
Sprint 3 Presentations 11/30 | STOCKO-20 | 10026 | STOCKO Sprint 3 | Story | 4 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:32 PM | 01/Sep/21 7:22 PM | 28/Sep/21 11:09 AM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0005r: |  |  |  |  | 10035 | Assignments/Presentations | To Do
Sprint 3 - Presentation PWEB update Project Video 11/23 | STOCKO-19 | 10025 | STOCKO Sprint 3 | Story | 4 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:31 PM | 01/Sep/21 7:22 PM | 28/Sep/21 11:09 AM |  |  | 0 |  | Sprint 3 Deliverables and PWEB update Project Video are Due |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0005j: |  |  |  |  | 10035 | Assignments/Presentations | To Do
Sprint 2 Presentation 10/26 | STOCKO-18 | 10024 | STOCKO Sprint 2 | Story | 4 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:31 PM | 01/Sep/21 7:21 PM | 28/Sep/21 11:09 AM |  |  | 0 |  | Sprint 2 Deliverables are Due |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0005b: |  |  |  |  | 10035 | Assignments/Presentations | To Do
Sprint 1 Presentation 9/28 | STOCKO-17 | 10023 | STOCKO Sprint 1 | Story | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:31 PM | 28/Sep/21 6:05 AM | 27/Sep/21 3:37 PM | 28/Sep/21 6:05 AM |  | 0 |  | Sprint 1 Deliverables are Due |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j:009 |  |  |  |  | 10035 | Assignments/Presentations | Done
Build Documentation on Running Locally. | STOCKO-16 | 10022 | STOCKO Sprint 1 | Ticket | 3 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 5:29 PM | 26/Sep/21 9:09 PM | 28/Sep/21 11:09 AM | 26/Sep/21 9:09 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001q:6 |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Create Branches for Dev, Test, and Prod | STOCKO-15 | 10021 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | High | Done | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:46 PM | 02/Sep/21 6:40 PM | 28/Sep/21 11:09 AM | 29/Aug/21 8:25 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001q:r |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Release a PROD version on Github | STOCKO-14 | 10020 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | High | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:46 PM | 16/Sep/21 7:09 PM | 28/Sep/21 11:09 AM | 16/Sep/21 7:09 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001o:zzi |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Initial project presentation Due 9/2/2021 | STOCKO-13 | 10019 | STOCKO Sprint 1 | Story | 5 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:45 PM | 07/Sep/21 4:16 PM | 09/Sep/21 8:25 PM | 07/Sep/21 4:16 PM |  | 0 |  | Project Pitch |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001l: |  | 26/Aug/21 7:09 PM;60c2917a946928007011d4ae;* 7 min Max, 5 min prefereed * Will be on Zoom * Everyone Must Speak * Comment on pitches on google drive * 1 Slide with Name and Members * 2-3 Slides on Audience and Importance * 1-2 slides on description of possible features * 1-2 slides on technical details and apis * 1 slide related app competitor app * 1-2 slides possible challenges | 31/Aug/21 7:56 PM;60c2917a946928007011d4ae;Is no longer on Zoom |  | 10035 | Assignments/Presentations | Done
[Enabler] How can we back-test how stock recommendations? | STOCKO-12 | 10018 |  | Ticket | 8 | To Do | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium |  | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:43 PM | 21/Sep/21 5:06 PM | 21/Sep/21 5:06 PM |  |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001o:y |  |  |  |  | 10036 | Stock Back-Testing | To Do
Add Basic CSS/SaSS Formatting | STOCKO-11 | 10017 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | High | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:34 PM | 02/Sep/21 6:40 PM | 28/Sep/21 11:09 AM | 31/Aug/21 8:55 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001q: |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Init Angular Application | STOCKO-10 | 10016 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | High | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:34 PM | 02/Sep/21 6:39 PM | 28/Sep/21 11:09 AM | 31/Aug/21 8:55 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001p: |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Init Git Repo | STOCKO-9 | 10015 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | High | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:33 PM | 08/Sep/21 1:02 AM | 28/Sep/21 11:09 AM | 29/Aug/21 8:25 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001k: |  |  |  |  | 10037 | Bootstrap Repo and Website | Done
Init Github Repo | STOCKO-8 | 10014 |  | Story |  | Obsolete | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:32 PM | 26/Aug/21 4:42 PM | 28/Sep/21 11:09 AM | 26/Aug/21 4:42 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i00033: | [6 empty] | Done
Backend Stock Processing | STOCKO-7 | 10013 | STOCKO Sprint 1 | Story |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done |  |  | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:32 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:14 AM | 26/Aug/21 6:14 PM |  | 0 | Obsolete |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001f: |  |  |  |  | 10031 | Backend Stock Processing | Done
[Enabler] determine how to store user positions | STOCKO-6 | 10012 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:30 PM | 02/Sep/21 2:25 PM | 28/Sep/21 11:09 AM | 02/Sep/21 2:25 PM |  | 0 |  |  |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001u: |  |  |  |  | 10034 | Positions DB | Done
Bootstrap Flask API to Run Locally | STOCKO-5 | 10011 | STOCKO Sprint 1 | Ticket | 2 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brendan Lucich | 5d66d0bae90c310c172250d0 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:29 PM | 13/Sep/21 4:50 PM | 28/Sep/21 6:16 AM | 13/Sep/21 4:49 PM |  | 0 |  | Bootstrap a Flask API (python backend) to handle necessary GETS/POST REQUESTS. * Potentially Login * Ticker Symbols * User’s Personal Position Manipulation |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0002m: |  |  |  |  | 10039 | Bootstrap APIs | Done
Login Authentication Portal | STOCKO-4 | 10010 | STOCKO Sprint 1 | Story |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:29 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:14 AM | 08/Sep/21 11:14 PM |  | 0 | Obsolete | Create a process for the user to login to their account |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001c: |  |  |  |  | 10029 | User Accounts | Done
User Account Creation | STOCKO-3 | 10009 | STOCKO Sprint 1 | Story |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Andrew Setka | 5b86f0acfa38ae2c89607b8b | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:28 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:15 AM | 08/Sep/21 11:17 PM |  | 0 | Obsolete | Create a process for the creation of user accounts |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001b:9 |  |  |  |  | 10029 | User Accounts | Done
[Enabler] Determine how stock data will be sourced | STOCKO-2 | 10008 | STOCKO Sprint 1 | Ticket | 1 | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Brady Mack | 5e1f420fd152ca0c9e193703 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:28 PM | 02/Sep/21 6:39 PM | 28/Sep/21 11:09 AM | 02/Sep/21 6:37 PM |  | 0 |  | Determine if we can gain access to BB/Yahoo/etc APIs or will we web-scrape for stock data? |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001p:i |  | 26/Aug/21 6:25 PM;60c2917a946928007011d4ae;Research APIs to see what can get the best data and no cost. Web scrapping may be the way to go if BB does not come through. |  |  | 10033 | Backend to Datasource API/Webscrapping | Done
Bootstrap Website/GIT | STOCKO-1 | 10007 | STOCKO Sprint 1 | Story |  | Done | STOCKO | STOCKO | software | Brendan Lucich | 60c2917a946928007011d4ae |  | Medium | Done | Alex Davis | 5b86f28907d9482bd98ae887 | Brendan Lucich | 60c2917a946928007011d4ae | Brendan Lucich | 60c2917a946928007011d4ae | 26/Aug/21 4:21 PM | 28/Sep/21 6:16 AM | 28/Sep/21 6:13 AM | 26/Aug/21 6:07 PM |  | 0 | Obsolete | Bootstrap Website for Capstone Project |  | Brendan Lucich |  | 60c2917a946928007011d4ae | [11 empty] | {} |  | 0¦i0001j: |  |  |  |  | 10030 | Website App Frontend/UI | Done